## Sheet1
Risk ID | Date Identified | Category | Risk Description | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score (G×H) | Priority | NIST Control (800-53 Rev.5) | ISO 27001:2022 Annex A Control | Loi 25 Reference | Current Control in Place | Recommendation | Owner | Status
R-001 | 2026-07-02 | Identity & Access Management | One or more user accounts have PasswordNeverExpires set to True in Active Directory, allowing credentials to remain valid indefinitely without forced renewal | External attacker performing brute force attack against accounts with non-expiring passwords | No password expiry policy is enforced in Active Directory , accounts retain the same credentials indefinitely with no forced rotation | 4 | 4 | 16 | High | IA-5 Authenticator Management | A.5.17 Authentication information | Art. 10 | Nothing | GPO to limit passwords'lifetime | IT Department | In progress
R-002 | 2026-07-07 | Identity & Access Management | Account lockout threshold is configured to 0 in Active Directory Group Policy, meaning unlimited failed login attempts are permitted with no automatic account protection mechanism | External attacker conducting automated brute force or password spray attack against Active Directory accounts | A threat actor could indefinitely log in to the system without being detected . | 4 | 4 | 16 | High | AC-7 (Unsuccessful Login Attempts) | A.8.5 (Secure log-on procedures) | Art. 10 | Nothing | GPO for lockout threshold | IT Department | In progress
R-003 | 2026-07-07 | Identity & Access Management | Password complexity requirements are not enforced via Group Policy, allowing users to create simple passwords without uppercase, numbers, or symbols | External attacker performing dictionary or brute force attack exploiting accounts with no complexity requirements | No Group Policy enforcing password complexity rules - users can set passwords like '1234' or 'password'. | 3 | 4 | 12 | High | IA-5(1) (Password-Based Authentication) | A.5.17 Authentication Information | Art. 10 | Nothing | GPO to enhance passwords' complexity | IT Department | In progress
R-004 | 2026-07-07 | Audit & Monitoring | No AD logging or monitoring . The enterprise is completely blind regarding suspicious activities on their network . | A hacker / an emloyee could try to access unauthorized ressources without permission and conducting data exfiltration. | All activities , wether they are malicious or normal aren't monitored , everything is unrecored . | 4 | 5 | 20 | Critical | AU-2 Event Logging | A.8.15 Logging | Art. 3.5–3.8 | Nothing | Enable AD audit logging for logon events Evaluate SIEM deployment (Wazuh or Splunk) | IT Department | In progress
R-005 | 2026-07-07 | Identity & Access Management | The password maximum age is set to 90 , so strong passwords need to be reset after 90 days .Anyone could change a password for a weak one . | If the passwords strenght is reduced , attackers could easily break them and exfiltrate data . | Employees could potentially change their password from a strong to a weak one . | 3 | 4 | 16 | High | IA-5(1): Password-Based Authentication | A.8.5 Secure log-on procedures | Art 10 | Nothing | Set the password minimun age from 90 to 0 | IT Department | In progress
R-006 | 2026-07-07 | Identity & Access Management | Multi-Factor Authentication (MFA) is not implemented for any user account in the Active Directory environment | External attacker who has obtained valid credentials through phishing or brute force can authenticate successfully with no additional verification barrier | No second authentication factor is required, a stolen or guessed password alone is sufficient to gain full access to any user account | 4 | 4 | 16 | Hight | IA-2: Identification and Authentication | A.8.5 Secure log-on procedures | Art 10 | Nothing | Activate the MFA for every account in the enterprise | IT Department | In progress